## 表1
序号 | 设备编号 | 起始时间 | 结束时间 | 持续工作时间(s) | 工序编号
1 | Automated Conveying Arm1-1 | 00:03:20 | 01:15:20 | 4320 | A1
2 | Precision Filling Machine1-1 | 00:03:20 | 01:33:20 | 5400 | A1
3 | Industrial Cleaning Machine1-1 | 01:33:20 | 03:33:20 | 7200 | A2
4 | High-speed Polishing Machine1-1 | 01:33:20 | 06:33:20 | 18000 | A2
5 | Automatic Sensing Multi-Function Machine1-1 | 06:33:20 | 11:33:20 | 18000 | A3

## 表2
序号 | 设备编号 | 起始时间 | 结束时间 | 持续工作时间(s) | 工序编号
1 | Automated Conveying Arm1-2 | 00:03:20 | 01:15:20 | 4320 | A1
2 | Precision Filling Machine1-1 | 00:03:20 | 01:33:20 | 5400 | A1
3 | Industrial Cleaning Machine1-3 | 00:03:20 | 04:03:20 | 14400 | E1
4 | Automated Conveying Arm1-1 | 00:03:50 | 02:56:38 | 10368 | C1
5 | Industrial Cleaning Machine1-2 | 00:03:50 | 02:56:38 | 10368 | C1
6 | Industrial Cleaning Machine1-4 | 00:05:10 | 01:17:10 | 4320 | B1
7 | Industrial Cleaning Machine1-1 | 00:05:55 | 02:29:55 | 8640 | D1
8 | Automated Conveying Arm1-3 | 01:17:10 | 06:17:10 | 18000 | B2
9 | Precision Filling Machine1-4 | 01:17:10 | 08:47:10 | 27000 | B2
10 | Industrial Cleaning Machine1-5 | 01:33:20 | 03:33:20 | 7200 | A2
11 | High-speed Polishing Machine1-1 | 01:33:20 | 06:33:20 | 18000 | A2
12 | Automated Conveying Arm1-2 | 02:29:55 | 05:09:55 | 9600 | D2
13 | Precision Filling Machine1-2 | 02:29:55 | 06:29:55 | 14400 | D2
14 | Precision Filling Machine1-1 | 02:56:38 | 05:00:04 | 7406 | C2
15 | Precision Filling Machine1-3 | 04:03:20 | 05:46:12 | 6172 | E2
16 | Automated Conveying Arm1-1 | 05:00:04 | 06:26:28 | 5184 | C3
17 | Precision Filling Machine1-1 | 05:00:04 | 06:48:04 | 6480 | C3
18 | Industrial Cleaning Machine1-3 | 05:46:12 | 11:46:12 | 21600 | E3
19 | Precision Filling Machine1-2 | 06:29:55 | 07:47:04 | 4629 | D3
20 | High-speed Polishing Machine1-1 | 06:48:04 | 10:08:04 | 12000 | C4
21 | Industrial Cleaning Machine1-2 | 06:48:04 | 10:48:04 | 14400 | C4
22 | Automatic Sensing Multi-Function Machine1-1 | 07:47:04 | 12:47:04 | 18000 | D4
23 | Precision Filling Machine1-4 | 08:47:10 | 09:48:53 | 3703 | B3
24 | High-speed Polishing Machine1-1 | 10:12:24 | 22:42:24 | 45000 | D4
25 | Automatic Sensing Multi-Function Machine1-1 | 12:51:24 | 16:51:24 | 14400 | C5
26 | Automated Conveying Arm1-1 | 16:51:24 | 18:17:48 | 5184 | C3
27 | Precision Filling Machine1-1 | 16:51:24 | 18:39:24 | 6480 | C3
28 | Automatic Sensing Multi-Function Machine1-1 | 17:00:09 | 22:00:09 | 18000 | A3
29 | Industrial Cleaning Machine1-2 | 18:39:24 | 22:39:24 | 14400 | C4
30 | Automatic Sensing Multi-Function Machine1-1 | 22:08:39 | 25:44:39 | 12960 | B4
31 | High-speed Polishing Machine1-1 | 22:46:44 | 26:06:44 | 12000 | C4
32 | Automatic Sensing Multi-Function Machine1-1 | 26:06:44 | 30:06:44 | 14400 | C5
33 | High-speed Polishing Machine1-1 | 26:15:54 | 29:15:54 | 10800 | B4
34 | Automated Conveying Arm1-1 | 30:06:44 | 31:33:08 | 5184 | C3
35 | Precision Filling Machine1-1 | 30:06:44 | 31:54:44 | 6480 | C3
36 | Automatic Sensing Multi-Function Machine1-1 | 30:11:04 | 35:11:04 | 18000 | D5
37 | High-speed Polishing Machine1-1 | 31:54:44 | 35:14:44 | 12000 | C4
38 | Industrial Cleaning Machine1-2 | 31:54:44 | 35:54:44 | 14400 | C4
39 | High-speed Polishing Machine1-1 | 35:19:04 | 42:19:04 | 25200 | D6
40 | Automatic Sensing Multi-Function Machine1-1 | 35:19:39 | 37:19:39 | 7200 | E3
41 | Automatic Sensing Multi-Function Machine1-1 | 37:26:44 | 41:26:44 | 14400 | C5

## 表3
序号 | 设备编号 | 起始时间 | 结束时间 | 持续工作时间(s) | 工序编号 | 班组
1 | Automated Conveying Arm1-2 | 00:03:20 | 01:15:20 | 4320 | A1 | 班组1
2 | Precision Filling Machine1-2 | 00:03:20 | 01:33:20 | 5400 | A1 | 班组1
3 | Industrial Cleaning Machine1-2 | 00:03:20 | 04:03:20 | 14400 | E1 | 班组1
4 | Industrial Cleaning Machine2-2 | 00:03:50 | 01:15:50 | 4320 | B1 | 班组2
5 | Automated Conveying Arm1-1 | 00:03:50 | 02:56:38 | 10368 | C1 | 班组1
6 | Industrial Cleaning Machine1-1 | 00:03:50 | 02:56:38 | 10368 | C1 | 班组1
7 | Industrial Cleaning Machine2-1 | 00:05:40 | 02:29:40 | 8640 | D1 | 班组2
8 | Automated Conveying Arm2-2 | 01:15:50 | 06:15:50 | 18000 | B2 | 班组2
9 | Precision Filling Machine2-2 | 01:15:50 | 08:45:50 | 27000 | B2 | 班组2
10 | Industrial Cleaning Machine1-3 | 01:33:20 | 03:33:20 | 7200 | A2 | 班组1
11 | Automated Conveying Arm2-1 | 02:29:40 | 05:09:40 | 9600 | D2 | 班组2
12 | Precision Filling Machine2-1 | 02:29:40 | 06:29:40 | 14400 | D2 | 班组2
13 | Precision Filling Machine1-1 | 02:56:38 | 05:00:04 | 7406 | C2 | 班组1
14 | Precision Filling Machine1-3 | 04:03:20 | 05:46:12 | 6172 | E2 | 班组1
15 | Automated Conveying Arm1-1 | 05:00:04 | 06:26:28 | 5184 | C3 | 班组1
16 | Precision Filling Machine1-1 | 05:00:04 | 06:48:04 | 6480 | C3 | 班组1
17 | Industrial Cleaning Machine1-2 | 05:46:12 | 11:46:12 | 21600 | E3 | 班组1
18 | Precision Filling Machine2-1 | 06:29:40 | 07:46:49 | 4629 | D3 | 班组2
19 | High-speed Polishing Machine1-1 | 06:48:04 | 10:08:04 | 12000 | C4 | 班组1
20 | Industrial Cleaning Machine1-1 | 06:48:04 | 10:48:04 | 14400 | C4 | 班组1
21 | Automatic Sensing Multi-Function Machine2-1 | 07:46:49 | 12:46:49 | 18000 | D4 | 班组2
22 | High-speed Polishing Machine2-1 | 07:46:49 | 20:16:49 | 45000 | D4 | 班组2
23 | Precision Filling Machine2-2 | 08:45:50 | 09:47:33 | 3703 | B3 | 班组2
24 | Automatic Sensing Multi-Function Machine1-1 | 10:48:04 | 14:48:04 | 14400 | C5 | 班组1
25 | Automated Conveying Arm1-1 | 14:48:04 | 16:14:28 | 5184 | C3 | 班组1
26 | Precision Filling Machine1-1 | 14:48:04 | 16:36:04 | 6480 | C3 | 班组1
27 | High-speed Polishing Machine1-1 | 16:36:04 | 19:56:04 | 12000 | C4 | 班组1
28 | Industrial Cleaning Machine1-1 | 16:36:04 | 20:36:04 | 14400 | C4 | 班组1
29 | High-speed Polishing Machine1-1 | 20:04:49 | 25:04:49 | 18000 | A2 | 班组1
30 | Automatic Sensing Multi-Function Machine2-1 | 20:16:49 | 25:16:49 | 18000 | D5 | 班组2
31 | Automatic Sensing Multi-Function Machine1-1 | 20:36:04 | 24:36:04 | 14400 | C5 | 班组1
32 | Automated Conveying Arm1-1 | 24:36:04 | 26:02:28 | 5184 | C3 | 班组1
33 | Precision Filling Machine1-1 | 24:36:04 | 26:24:04 | 6480 | C3 | 班组1
34 | Automatic Sensing Multi-Function Machine1-1 | 24:43:09 | 26:43:09 | 7200 | E3 | 班组1
35 | High-speed Polishing Machine1-1 | 25:16:49 | 32:16:49 | 25200 | D6 | 班组1
36 | Automatic Sensing Multi-Function Machine2-1 | 25:24:19 | 30:24:19 | 18000 | A3 | 班组2
37 | High-speed Polishing Machine2-1 | 26:24:04 | 29:44:04 | 12000 | C4 | 班组2
38 | Industrial Cleaning Machine1-1 | 26:24:04 | 30:24:04 | 14400 | C4 | 班组1
39 | High-speed Polishing Machine2-1 | 29:53:14 | 32:53:14 | 10800 | B4 | 班组2
40 | Automatic Sensing Multi-Function Machine1-1 | 30:24:04 | 34:24:04 | 14400 | C5 | 班组1
41 | Automatic Sensing Multi-Function Machine2-1 | 30:32:49 | 34:08:49 | 12960 | B4 | 班组2

## 表4
序号 | 设备编号 | 起始时间 | 结束时间 | 持续工作时间(s) | 工序编号 | 班组
1 | Automated Conveying Arm1-2 | 00:03:20 | 01:15:20 | 4320 | A1 | 班组1
2 | Precision Filling Machine1-2 | 00:03:20 | 01:33:20 | 5400 | A1 | 班组1
3 | Industrial Cleaning Machine1-2 | 00:03:20 | 04:03:20 | 14400 | E1 | 班组1
4 | Industrial Cleaning Machine2-2 | 00:03:50 | 01:15:50 | 4320 | B1 | 班组2
5 | Automated Conveying Arm1-1 | 00:03:50 | 02:56:38 | 10368 | C1 | 班组1
6 | Industrial Cleaning Machine1-1 | 00:03:50 | 02:56:38 | 10368 | C1 | 班组1
7 | Industrial Cleaning Machine2-1 | 00:05:40 | 02:29:40 | 8640 | D1 | 班组2
8 | Automated Conveying Arm2-2 | 01:15:50 | 06:15:50 | 18000 | B2 | 班组2
9 | Precision Filling Machine2-2 | 01:15:50 | 08:45:50 | 27000 | B2 | 班组2
10 | Industrial Cleaning Machine1-3 | 01:33:20 | 03:33:20 | 7200 | A2 | 班组1
11 | Automated Conveying Arm2-1 | 02:29:40 | 05:09:40 | 9600 | D2 | 班组2
12 | Precision Filling Machine2-1 | 02:29:40 | 06:29:40 | 14400 | D2 | 班组2
13 | Precision Filling Machine1-1 | 02:56:38 | 05:00:04 | 7406 | C2 | 班组1
14 | Precision Filling Machine1-3 | 04:03:20 | 05:46:12 | 6172 | E2 | 班组1
15 | Automated Conveying Arm1-1 | 05:00:04 | 06:26:28 | 5184 | C3 | 班组1
16 | Precision Filling Machine1-1 | 05:00:04 | 06:48:04 | 6480 | C3 | 班组1
17 | Industrial Cleaning Machine1-2 | 05:46:12 | 11:46:12 | 21600 | E3 | 班组1
18 | Precision Filling Machine2-1 | 06:29:40 | 07:46:49 | 4629 | D3 | 班组2
19 | High-speed Polishing Machine1-1 | 06:48:04 | 10:08:04 | 12000 | C4 | 班组1
20 | Industrial Cleaning Machine1-1 | 06:48:04 | 10:48:04 | 14400 | C4 | 班组1
21 | Automatic Sensing Multi-Function Machine2-1 | 07:46:49 | 12:46:49 | 18000 | D4 | 班组2
22 | High-speed Polishing Machine2-1 | 07:46:49 | 20:16:49 | 45000 | D4 | 班组2
23 | Precision Filling Machine2-2 | 08:45:50 | 09:47:33 | 3703 | B3 | 班组2
24 | Automatic Sensing Multi-Function Machine1-1 | 10:48:04 | 14:48:04 | 14400 | C5 | 班组1
25 | Automated Conveying Arm1-1 | 14:48:04 | 16:14:28 | 5184 | C3 | 班组1
26 | Precision Filling Machine1-1 | 14:48:04 | 16:36:04 | 6480 | C3 | 班组1
27 | High-speed Polishing Machine1-1 | 16:36:04 | 19:56:04 | 12000 | C4 | 班组1
28 | Industrial Cleaning Machine1-1 | 16:36:04 | 20:36:04 | 14400 | C4 | 班组1
29 | High-speed Polishing Machine1-1 | 20:04:49 | 25:04:49 | 18000 | A2 | 班组1
30 | Automatic Sensing Multi-Function Machine2-1 | 20:16:49 | 25:16:49 | 18000 | D5 | 班组2
31 | Automatic Sensing Multi-Function Machine1-1 | 20:36:04 | 24:36:04 | 14400 | C5 | 班组1
32 | Automated Conveying Arm1-1 | 24:36:04 | 26:02:28 | 5184 | C3 | 班组1
33 | Precision Filling Machine1-1 | 24:36:04 | 26:24:04 | 6480 | C3 | 班组1
34 | Automatic Sensing Multi-Function Machine1-1 | 24:43:09 | 26:43:09 | 7200 | E3 | 班组1
35 | High-speed Polishing Machine1-1 | 25:16:49 | 32:16:49 | 25200 | D6 | 班组1
36 | Automatic Sensing Multi-Function Machine2-1 | 25:24:19 | 30:24:19 | 18000 | A3 | 班组2
37 | High-speed Polishing Machine2-1 | 26:24:04 | 29:44:04 | 12000 | C4 | 班组2
38 | Industrial Cleaning Machine1-1 | 26:24:04 | 30:24:04 | 14400 | C4 | 班组1
39 | High-speed Polishing Machine2-1 | 29:53:14 | 32:53:14 | 10800 | B4 | 班组2
40 | Automatic Sensing Multi-Function Machine1-1 | 30:24:04 | 34:24:04 | 14400 | C5 | 班组1
41 | Automatic Sensing Multi-Function Machine2-1 | 30:32:49 | 34:08:49 | 12960 | B4 | 班组2

## 表5
设备名称 | 班组1购买台数 | 班组2购买台数
自动化输送臂 | 0 | 0
工业清洗机 | 0 | 0
精密灌装机 | 0 | 0
自动传感多功能机 | 0 | 0
高速抛光机 | 0 | 0

## 问题1完整排程
问题 | 序号 | 设备编号 | 设备类型 | 班组 | 班组名称 | 是否新购 | 车间 | 原始工序编号 | 内部工序编号 | 起始秒 | 结束秒 | 起始时间 | 结束时间 | 持续工作时间(s) | 运输时间(s)
问题1 | 1 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 4520 | 00:03:20 | 01:15:20 | 4320 | 200
问题1 | 2 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 5600 | 00:03:20 | 01:33:20 | 5400 | 200
问题1 | 3 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 12800 | 01:33:20 | 03:33:20 | 7200 | 200
问题1 | 4 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 23600 | 01:33:20 | 06:33:20 | 18000 | 200
问题1 | 5 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | A | A3 | A3 | 23600 | 41600 | 06:33:20 | 11:33:20 | 18000 | 200

## 问题2完整排程
问题 | 序号 | 设备编号 | 设备类型 | 班组 | 班组名称 | 是否新购 | 车间 | 原始工序编号 | 内部工序编号 | 起始秒 | 结束秒 | 起始时间 | 结束时间 | 持续工作时间(s) | 运输时间(s)
问题2 | 1 | Automated Conveying Arm1-2 | Automated Conveying Arm | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 4520 | 00:03:20 | 01:15:20 | 4320 | 200
问题2 | 2 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 5600 | 00:03:20 | 01:33:20 | 5400 | 200
问题2 | 3 | Industrial Cleaning Machine1-3 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E1 | E1 | 200 | 14600 | 00:03:20 | 04:03:20 | 14400 | 200
问题2 | 4 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题2 | 5 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题2 | 6 | Industrial Cleaning Machine1-4 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | B | B1 | B1 | 310 | 4630 | 00:05:10 | 01:17:10 | 4320 | 310
问题2 | 7 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | D | D1 | D1 | 355 | 8995 | 00:05:55 | 02:29:55 | 8640 | 355
问题2 | 8 | Automated Conveying Arm1-3 | Automated Conveying Arm | 1 | 班组1 | FALSE | B | B2 | B2 | 4630 | 22630 | 01:17:10 | 06:17:10 | 18000 | 310
问题2 | 9 | Precision Filling Machine1-4 | Precision Filling Machine | 1 | 班组1 | FALSE | B | B2 | B2 | 4630 | 31630 | 01:17:10 | 08:47:10 | 27000 | 310
问题2 | 10 | Industrial Cleaning Machine1-5 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 12800 | 01:33:20 | 03:33:20 | 7200 | 200
问题2 | 11 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 23600 | 01:33:20 | 06:33:20 | 18000 | 200
问题2 | 12 | Automated Conveying Arm1-2 | Automated Conveying Arm | 1 | 班组1 | FALSE | D | D2 | D2 | 8995 | 18595 | 02:29:55 | 05:09:55 | 9600 | 450
问题2 | 13 | Precision Filling Machine1-2 | Precision Filling Machine | 1 | 班组1 | FALSE | D | D2 | D2 | 8995 | 23395 | 02:29:55 | 06:29:55 | 14400 | 355
问题2 | 14 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C2 | C2 | 10598 | 18004 | 02:56:38 | 05:00:04 | 7406 | 525
问题2 | 15 | Precision Filling Machine1-3 | Precision Filling Machine | 1 | 班组1 | FALSE | E | E2 | E2 | 14600 | 20772 | 04:03:20 | 05:46:12 | 6172 | 200
问题2 | 16 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 23188 | 05:00:04 | 06:26:28 | 5184 | 0
问题2 | 17 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 24484 | 05:00:04 | 06:48:04 | 6480 | 0
问题2 | 18 | Industrial Cleaning Machine1-3 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 20772 | 42372 | 05:46:12 | 11:46:12 | 21600 | 0
问题2 | 19 | Precision Filling Machine1-2 | Precision Filling Machine | 1 | 班组1 | FALSE | D | D3 | D3 | 23395 | 28024 | 06:29:55 | 07:47:04 | 4629 | 0
问题2 | 20 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 36484 | 06:48:04 | 10:08:04 | 12000 | 525
问题2 | 21 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 38884 | 06:48:04 | 10:48:04 | 14400 | 0
问题2 | 22 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | D | D4 | D4 | 28024 | 46024 | 07:47:04 | 12:47:04 | 18000 | 355
问题2 | 23 | Precision Filling Machine1-4 | Precision Filling Machine | 1 | 班组1 | FALSE | B | B3 | B3 | 31630 | 35333 | 08:47:10 | 09:48:53 | 3703 | 0
问题2 | 24 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | D | D4 | D4 | 36744 | 81744 | 10:12:24 | 22:42:24 | 45000 | 260
问题2 | 25 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-1 | 46284 | 60684 | 12:51:24 | 16:51:24 | 14400 | 260
问题2 | 26 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-2 | 60684 | 65868 | 16:51:24 | 18:17:48 | 5184 | 0
问题2 | 27 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-2 | 60684 | 67164 | 16:51:24 | 18:39:24 | 6480 | 0
问题2 | 28 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | A | A3 | A3 | 61209 | 79209 | 17:00:09 | 22:00:09 | 18000 | 525
问题2 | 29 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 67164 | 81564 | 18:39:24 | 22:39:24 | 14400 | 0
问题2 | 30 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | B | B4 | B4 | 79719 | 92679 | 22:08:39 | 25:44:39 | 12960 | 510
问题2 | 31 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 82004 | 94004 | 22:46:44 | 26:06:44 | 12000 | 260
问题2 | 32 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-2 | 94004 | 108404 | 26:06:44 | 30:06:44 | 14400 | 550
问题2 | 33 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | B | B4 | B4 | 94554 | 105354 | 26:15:54 | 29:15:54 | 10800 | 550
问题2 | 34 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-3 | 108404 | 113588 | 30:06:44 | 31:33:08 | 5184 | 0
问题2 | 35 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-3 | 108404 | 114884 | 30:06:44 | 31:54:44 | 6480 | 0
问题2 | 36 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | D | D5 | D5 | 108664 | 126664 | 30:11:04 | 35:11:04 | 18000 | 260
问题2 | 37 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-3 | 114884 | 126884 | 31:54:44 | 35:14:44 | 12000 | 550
问题2 | 38 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-3 | 114884 | 129284 | 31:54:44 | 35:54:44 | 14400 | 0
问题2 | 39 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | D | D6 | D6 | 127144 | 152344 | 35:19:04 | 42:19:04 | 25200 | 260
问题2 | 40 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 127179 | 134379 | 35:19:39 | 37:19:39 | 7200 | 515
问题2 | 41 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-3 | 134804 | 149204 | 37:26:44 | 41:26:44 | 14400 | 425

## 问题3完整排程
问题 | 序号 | 设备编号 | 设备类型 | 班组 | 班组名称 | 是否新购 | 车间 | 原始工序编号 | 内部工序编号 | 起始秒 | 结束秒 | 起始时间 | 结束时间 | 持续工作时间(s) | 运输时间(s)
问题3 | 1 | Automated Conveying Arm1-2 | Automated Conveying Arm | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 4520 | 00:03:20 | 01:15:20 | 4320 | 200
问题3 | 2 | Precision Filling Machine1-2 | Precision Filling Machine | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 5600 | 00:03:20 | 01:33:20 | 5400 | 200
问题3 | 3 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E1 | E1 | 200 | 14600 | 00:03:20 | 04:03:20 | 14400 | 200
问题3 | 4 | Industrial Cleaning Machine2-2 | Industrial Cleaning Machine | 2 | 班组2 | FALSE | B | B1 | B1 | 230 | 4550 | 00:03:50 | 01:15:50 | 4320 | 230
问题3 | 5 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题3 | 6 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题3 | 7 | Industrial Cleaning Machine2-1 | Industrial Cleaning Machine | 2 | 班组2 | FALSE | D | D1 | D1 | 340 | 8980 | 00:05:40 | 02:29:40 | 8640 | 340
问题3 | 8 | Automated Conveying Arm2-2 | Automated Conveying Arm | 2 | 班组2 | FALSE | B | B2 | B2 | 4550 | 22550 | 01:15:50 | 06:15:50 | 18000 | 230
问题3 | 9 | Precision Filling Machine2-2 | Precision Filling Machine | 2 | 班组2 | FALSE | B | B2 | B2 | 4550 | 31550 | 01:15:50 | 08:45:50 | 27000 | 230
问题3 | 10 | Industrial Cleaning Machine1-3 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 12800 | 01:33:20 | 03:33:20 | 7200 | 200
问题3 | 11 | Automated Conveying Arm2-1 | Automated Conveying Arm | 2 | 班组2 | FALSE | D | D2 | D2 | 8980 | 18580 | 02:29:40 | 05:09:40 | 9600 | 340
问题3 | 12 | Precision Filling Machine2-1 | Precision Filling Machine | 2 | 班组2 | FALSE | D | D2 | D2 | 8980 | 23380 | 02:29:40 | 06:29:40 | 14400 | 340
问题3 | 13 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C2 | C2 | 10598 | 18004 | 02:56:38 | 05:00:04 | 7406 | 230
问题3 | 14 | Precision Filling Machine1-3 | Precision Filling Machine | 1 | 班组1 | FALSE | E | E2 | E2 | 14600 | 20772 | 04:03:20 | 05:46:12 | 6172 | 200
问题3 | 15 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 23188 | 05:00:04 | 06:26:28 | 5184 | 0
问题3 | 16 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 24484 | 05:00:04 | 06:48:04 | 6480 | 0
问题3 | 17 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 20772 | 42372 | 05:46:12 | 11:46:12 | 21600 | 0
问题3 | 18 | Precision Filling Machine2-1 | Precision Filling Machine | 2 | 班组2 | FALSE | D | D3 | D3 | 23380 | 28009 | 06:29:40 | 07:46:49 | 4629 | 0
问题3 | 19 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 36484 | 06:48:04 | 10:08:04 | 12000 | 230
问题3 | 20 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 38884 | 06:48:04 | 10:48:04 | 14400 | 0
问题3 | 21 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | D | D4 | D4 | 28009 | 46009 | 07:46:49 | 12:46:49 | 18000 | 340
问题3 | 22 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | D | D4 | D4 | 28009 | 73009 | 07:46:49 | 20:16:49 | 45000 | 340
问题3 | 23 | Precision Filling Machine2-2 | Precision Filling Machine | 2 | 班组2 | FALSE | B | B3 | B3 | 31550 | 35253 | 08:45:50 | 09:47:33 | 3703 | 0
问题3 | 24 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-1 | 38884 | 53284 | 10:48:04 | 14:48:04 | 14400 | 230
问题3 | 25 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-2 | 53284 | 58468 | 14:48:04 | 16:14:28 | 5184 | 0
问题3 | 26 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-2 | 53284 | 59764 | 14:48:04 | 16:36:04 | 6480 | 0
问题3 | 27 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 59764 | 71764 | 16:36:04 | 19:56:04 | 12000 | 0
问题3 | 28 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 59764 | 74164 | 16:36:04 | 20:36:04 | 14400 | 0
问题3 | 29 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 72289 | 90289 | 20:04:49 | 25:04:49 | 18000 | 525
问题3 | 30 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | D | D5 | D5 | 73009 | 91009 | 20:16:49 | 25:16:49 | 18000 | 0
问题3 | 31 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-2 | 74164 | 88564 | 20:36:04 | 24:36:04 | 14400 | 0
问题3 | 32 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-3 | 88564 | 93748 | 24:36:04 | 26:02:28 | 5184 | 0
问题3 | 33 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-3 | 88564 | 95044 | 24:36:04 | 26:24:04 | 6480 | 0
问题3 | 34 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 88989 | 96189 | 24:43:09 | 26:43:09 | 7200 | 425
问题3 | 35 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | D | D6 | D6 | 91009 | 116209 | 25:16:49 | 32:16:49 | 25200 | 450
问题3 | 36 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | A | A3 | A3 | 91459 | 109459 | 25:24:19 | 30:24:19 | 18000 | 450
问题3 | 37 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | C | C4 | C4-3 | 95044 | 107044 | 26:24:04 | 29:44:04 | 12000 | 260
问题3 | 38 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-3 | 95044 | 109444 | 26:24:04 | 30:24:04 | 14400 | 0
问题3 | 39 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | B | B4 | B4 | 107594 | 118394 | 29:53:14 | 32:53:14 | 10800 | 550
问题3 | 40 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-3 | 109444 | 123844 | 30:24:04 | 34:24:04 | 14400 | 425
问题3 | 41 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | B | B4 | B4 | 109969 | 122929 | 30:32:49 | 34:08:49 | 12960 | 510

## 问题4完整排程
问题 | 序号 | 设备编号 | 设备类型 | 班组 | 班组名称 | 是否新购 | 车间 | 原始工序编号 | 内部工序编号 | 起始秒 | 结束秒 | 起始时间 | 结束时间 | 持续工作时间(s) | 运输时间(s)
问题4 | 1 | Automated Conveying Arm1-2 | Automated Conveying Arm | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 4520 | 00:03:20 | 01:15:20 | 4320 | 200
问题4 | 2 | Precision Filling Machine1-2 | Precision Filling Machine | 1 | 班组1 | FALSE | A | A1 | A1 | 200 | 5600 | 00:03:20 | 01:33:20 | 5400 | 200
问题4 | 3 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E1 | E1 | 200 | 14600 | 00:03:20 | 04:03:20 | 14400 | 200
问题4 | 4 | Industrial Cleaning Machine2-2 | Industrial Cleaning Machine | 2 | 班组2 | FALSE | B | B1 | B1 | 230 | 4550 | 00:03:50 | 01:15:50 | 4320 | 230
问题4 | 5 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题4 | 6 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C1 | C1 | 230 | 10598 | 00:03:50 | 02:56:38 | 10368 | 230
问题4 | 7 | Industrial Cleaning Machine2-1 | Industrial Cleaning Machine | 2 | 班组2 | FALSE | D | D1 | D1 | 340 | 8980 | 00:05:40 | 02:29:40 | 8640 | 340
问题4 | 8 | Automated Conveying Arm2-2 | Automated Conveying Arm | 2 | 班组2 | FALSE | B | B2 | B2 | 4550 | 22550 | 01:15:50 | 06:15:50 | 18000 | 230
问题4 | 9 | Precision Filling Machine2-2 | Precision Filling Machine | 2 | 班组2 | FALSE | B | B2 | B2 | 4550 | 31550 | 01:15:50 | 08:45:50 | 27000 | 230
问题4 | 10 | Industrial Cleaning Machine1-3 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 5600 | 12800 | 01:33:20 | 03:33:20 | 7200 | 200
问题4 | 11 | Automated Conveying Arm2-1 | Automated Conveying Arm | 2 | 班组2 | FALSE | D | D2 | D2 | 8980 | 18580 | 02:29:40 | 05:09:40 | 9600 | 340
问题4 | 12 | Precision Filling Machine2-1 | Precision Filling Machine | 2 | 班组2 | FALSE | D | D2 | D2 | 8980 | 23380 | 02:29:40 | 06:29:40 | 14400 | 340
问题4 | 13 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C2 | C2 | 10598 | 18004 | 02:56:38 | 05:00:04 | 7406 | 230
问题4 | 14 | Precision Filling Machine1-3 | Precision Filling Machine | 1 | 班组1 | FALSE | E | E2 | E2 | 14600 | 20772 | 04:03:20 | 05:46:12 | 6172 | 200
问题4 | 15 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 23188 | 05:00:04 | 06:26:28 | 5184 | 0
问题4 | 16 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-1 | 18004 | 24484 | 05:00:04 | 06:48:04 | 6480 | 0
问题4 | 17 | Industrial Cleaning Machine1-2 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 20772 | 42372 | 05:46:12 | 11:46:12 | 21600 | 0
问题4 | 18 | Precision Filling Machine2-1 | Precision Filling Machine | 2 | 班组2 | FALSE | D | D3 | D3 | 23380 | 28009 | 06:29:40 | 07:46:49 | 4629 | 0
问题4 | 19 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 36484 | 06:48:04 | 10:08:04 | 12000 | 230
问题4 | 20 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-1 | 24484 | 38884 | 06:48:04 | 10:48:04 | 14400 | 0
问题4 | 21 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | D | D4 | D4 | 28009 | 46009 | 07:46:49 | 12:46:49 | 18000 | 340
问题4 | 22 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | D | D4 | D4 | 28009 | 73009 | 07:46:49 | 20:16:49 | 45000 | 340
问题4 | 23 | Precision Filling Machine2-2 | Precision Filling Machine | 2 | 班组2 | FALSE | B | B3 | B3 | 31550 | 35253 | 08:45:50 | 09:47:33 | 3703 | 0
问题4 | 24 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-1 | 38884 | 53284 | 10:48:04 | 14:48:04 | 14400 | 230
问题4 | 25 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-2 | 53284 | 58468 | 14:48:04 | 16:14:28 | 5184 | 0
问题4 | 26 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-2 | 53284 | 59764 | 14:48:04 | 16:36:04 | 6480 | 0
问题4 | 27 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 59764 | 71764 | 16:36:04 | 19:56:04 | 12000 | 0
问题4 | 28 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-2 | 59764 | 74164 | 16:36:04 | 20:36:04 | 14400 | 0
问题4 | 29 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | A | A2 | A2 | 72289 | 90289 | 20:04:49 | 25:04:49 | 18000 | 525
问题4 | 30 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | D | D5 | D5 | 73009 | 91009 | 20:16:49 | 25:16:49 | 18000 | 0
问题4 | 31 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-2 | 74164 | 88564 | 20:36:04 | 24:36:04 | 14400 | 0
问题4 | 32 | Automated Conveying Arm1-1 | Automated Conveying Arm | 1 | 班组1 | FALSE | C | C3 | C3-3 | 88564 | 93748 | 24:36:04 | 26:02:28 | 5184 | 0
问题4 | 33 | Precision Filling Machine1-1 | Precision Filling Machine | 1 | 班组1 | FALSE | C | C3 | C3-3 | 88564 | 95044 | 24:36:04 | 26:24:04 | 6480 | 0
问题4 | 34 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | E | E3 | E3 | 88989 | 96189 | 24:43:09 | 26:43:09 | 7200 | 425
问题4 | 35 | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 1 | 班组1 | FALSE | D | D6 | D6 | 91009 | 116209 | 25:16:49 | 32:16:49 | 25200 | 450
问题4 | 36 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | A | A3 | A3 | 91459 | 109459 | 25:24:19 | 30:24:19 | 18000 | 450
问题4 | 37 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | C | C4 | C4-3 | 95044 | 107044 | 26:24:04 | 29:44:04 | 12000 | 260
问题4 | 38 | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 1 | 班组1 | FALSE | C | C4 | C4-3 | 95044 | 109444 | 26:24:04 | 30:24:04 | 14400 | 0
问题4 | 39 | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 2 | 班组2 | FALSE | B | B4 | B4 | 107594 | 118394 | 29:53:14 | 32:53:14 | 10800 | 550
问题4 | 40 | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 1 | 班组1 | FALSE | C | C5 | C5-3 | 109444 | 123844 | 30:24:04 | 34:24:04 | 14400 | 425
问题4 | 41 | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 2 | 班组2 | FALSE | B | B4 | B4 | 109969 | 122929 | 30:32:49 | 34:08:49 | 12960 | 510

## Summary
问题 | 精确最短时长(s) | 精确最短时长(HH:MM:SS) | 最晚完工车间 | 利用率最高设备类型 | 运输时间占比最高设备类型 | 备注 | 当前搜索最优可行时长(s) | 当前搜索最优可行时长(HH:MM:SS) | 问题4新购设备平均利用率
问题1 | 41600 | 11:33:20 | A | 自动传感多功能机 | 自动化输送臂 | A车间严格串行，枚举设备组合，精确最短时长
问题2 |  |  | D | 高速抛光机 | 自动传感多功能机 | TS+SA启发式搜索, iterations=54 | 152344 | 42:19:04
问题3 |  |  | C | 高速抛光机 | 自动传感多功能机 | 双班组联合调度, iterations=54 | 123844 | 34:24:04
问题4 |  |  | C | 高速抛光机 | 自动传感多功能机 | 费用=0; budget=500000, candidates=11, decoder=mixed, bottleneck=['高速抛光机', '自动传感多功能机', '工业清洗机'] | 123844 | 34:24:04 | 0
数据读取 | [5 empty] | 距离表=edge-list; 文件=./B-attachment.xlsx
C工序展开 | [5 empty] | 启用=True; 集合=['C3', 'C4', 'C5']; 次数=3
C工序展开 | [5 empty] | C工序展开配置: enabled=True, base_ops=['C3', 'C4', 'C5'], repeat=3. 该规则基于对附件 C3-C5 重复工程段的解释，用户应核对原始题目数据。
C工序展开 | [5 empty] | WARNING: C3 expanded into 3 sub-operations. Verify against original data.
C工序展开 | [5 empty] | WARNING: C4 expanded into 3 sub-operations. Verify against original data.
C工序展开 | [5 empty] | WARNING: C5 expanded into 3 sub-operations. Verify against original data.

## Feasibility
问题 | 检查项 | 是否通过 | 违规数量 | 说明
问题1 | 排程字段完整性 | TRUE | 0 | 完整
问题1 | 工序完整性 | TRUE | 0 | 每个工序出现次数与所需设备数一致
问题1 | 设备类型匹配 | TRUE | 0 | Counter 检查 required_types
问题1 | 设备类型逐行匹配 | TRUE | 0 | 每条记录设备类型满足工序
问题1 | 加工时长正确性 | TRUE | 0 | ceil(workload/efficiency)
问题1 | 工序顺序约束 | TRUE | 0 | 同一车间按内部顺序执行
问题1 | 设备不可重叠 | TRUE | 0 | 同一设备相邻作业不重叠
问题1 | 首次运输时间 | TRUE | 0 | 首任务从班组初始位置出发
问题1 | 跨车间运输时间 | TRUE | 0 | 后续任务留足运输
问题1 | 双设备工序完成规则 | TRUE | 0 | 双设备均完成完整工程量
问题1 | 问题4预算约束 | TRUE | 0 | 非问题4或未传入购置方案
问题2 | 排程字段完整性 | TRUE | 0 | 完整
问题2 | 工序完整性 | TRUE | 0 | 每个工序出现次数与所需设备数一致
问题2 | 设备类型匹配 | TRUE | 0 | Counter 检查 required_types
问题2 | 设备类型逐行匹配 | TRUE | 0 | 每条记录设备类型满足工序
问题2 | 加工时长正确性 | TRUE | 0 | ceil(workload/efficiency)
问题2 | 工序顺序约束 | TRUE | 0 | 同一车间按内部顺序执行
问题2 | 设备不可重叠 | TRUE | 0 | 同一设备相邻作业不重叠
问题2 | 首次运输时间 | TRUE | 0 | 首任务从班组初始位置出发
问题2 | 跨车间运输时间 | TRUE | 0 | 后续任务留足运输
问题2 | 双设备工序完成规则 | TRUE | 0 | 双设备均完成完整工程量
问题2 | 问题4预算约束 | TRUE | 0 | 非问题4或未传入购置方案
问题3 | 排程字段完整性 | TRUE | 0 | 完整
问题3 | 工序完整性 | TRUE | 0 | 每个工序出现次数与所需设备数一致
问题3 | 设备类型匹配 | TRUE | 0 | Counter 检查 required_types
问题3 | 设备类型逐行匹配 | TRUE | 0 | 每条记录设备类型满足工序
问题3 | 加工时长正确性 | TRUE | 0 | ceil(workload/efficiency)
问题3 | 工序顺序约束 | TRUE | 0 | 同一车间按内部顺序执行
问题3 | 设备不可重叠 | TRUE | 0 | 同一设备相邻作业不重叠
问题3 | 首次运输时间 | TRUE | 0 | 首任务从班组初始位置出发
问题3 | 跨车间运输时间 | TRUE | 0 | 后续任务留足运输
问题3 | 双设备工序完成规则 | TRUE | 0 | 双设备均完成完整工程量
问题3 | 问题4预算约束 | TRUE | 0 | 非问题4或未传入购置方案
问题4 | 排程字段完整性 | TRUE | 0 | 完整
问题4 | 工序完整性 | TRUE | 0 | 每个工序出现次数与所需设备数一致
问题4 | 设备类型匹配 | TRUE | 0 | Counter 检查 required_types
问题4 | 设备类型逐行匹配 | TRUE | 0 | 每条记录设备类型满足工序
问题4 | 加工时长正确性 | TRUE | 0 | ceil(workload/efficiency)
问题4 | 工序顺序约束 | TRUE | 0 | 同一车间按内部顺序执行
问题4 | 设备不可重叠 | TRUE | 0 | 同一设备相邻作业不重叠
问题4 | 首次运输时间 | TRUE | 0 | 首任务从班组初始位置出发
问题4 | 跨车间运输时间 | TRUE | 0 | 后续任务留足运输
问题4 | 双设备工序完成规则 | TRUE | 0 | 双设备均完成完整工程量
问题4 | 问题4预算约束 | TRUE | 0 | 费用=0, 预算=500000

## 理论下界对比
问题 | 关键路径下界(s) | 设备负载下界(s) | 静态瓶颈负载下界(s) | 综合下界(s) | 本文可行解(s) | gap | gap百分比 | 说明
问题1 | 41400 | 18000 | 18000 | 41400 | 41600 | 0.0048309 | 0.0048309 | 综合下界未计入运输时间，为乐观下界
问题2 | 123614 | 135000 | 135000 | 135000 | 152344 | 0.12847 | 0.12847 | 综合下界未计入运输时间，为乐观下界
问题3 | 123614 | 67500 | 67500 | 123614 | 123844 | 0.0018606 | 0.0018606 | 综合下界未计入运输时间，为乐观下界
问题4 | 123614 | 67500 | 67500 | 123614 | 123844 | 0.0018606 | 0.0018606 | 综合下界未计入运输时间，为乐观下界

## 基准规则对比
问题 | 本文启发式搜索(s) | A→E串行(s) | 最快设备优先(s) | 最近可用设备优先(s) | 最早可用设备优先(s) | 最早完成优先(s) | 相对A→E串行改善率 | 相对最快设备优先改善率 | 相对最近可用设备优先改善率 | 相对最早可用设备优先改善率 | 相对最早完成优先改善率
问题2 | 152344 | 215303 | 209083 | 209083 | 209083 | 165890 | 0.29242 | 0.27137 | 0.27137 | 0.27137 | 0.081657
问题3 | 123844 | 135068 | 143684 | 188667 | 143684 | 135068 | 0.083099 | 0.13808 | 0.34358 | 0.13808 | 0.083099
问题4 | 123844 | 135068 | 143684 | 188667 | 143684 | 135068 | 0.083099 | 0.13808 | 0.34358 | 0.13808 | 0.083099

## 模型求解说明
主题 | 说明
问题1最优性 | A车间严格串行，枚举设备组合，精确最短时长
问题2-4最优性声明 | 多策略启发式+Tabu-SA局部搜索，不声称全局最优
算法改进 | Tabu Search + Simulated Annealing + CPM-aware邻域 + Active Decoder
可信度支撑 | 可行性检查、理论下界、基准对比、瓶颈统计

## 调度策略诊断
问题 | decoder | best decoder | 瓶颈设备类型 | 瓶颈来源 | 静态瓶颈 | 车间权重 | TS+SA改进 | BN-TS+SA改进 | best strategy
问题2 | mixed | active | 高速抛光机；自动传感多功能机 | dynamic | 高速抛光机；自动传感多功能机 | A:0.397；B:1.000；C:0.713；D:0.381；E:0.000 | 2 | 0 | critical_path_first+active+TS-SA
问题3 | mixed | append | 高速抛光机；自动传感多功能机 | dynamic | 高速抛光机；自动传感多功能机 | A:0.480；B:0.967；C:1.000；D:0.724；E:0.000 | 0 | 0 | critical_path_first+append
问题4 | mixed | append | 高速抛光机；自动传感多功能机 | dynamic | 高速抛光机；自动传感多功能机 | A:0.480；B:0.967；C:1.000；D:0.724；E:0.000 | 0 | 0 | critical_path_first+append

## 效率单位识别说明
工序编号 | 设备类型 | 原始效率文本 | 解析数值 | 单位判断 | 转换后每秒效率
A1 | 自动化输送臂 | Precision Filling Machine 200m³/h and Automated Conveying Arm 250m³/h | 250 | per hour; divided by 3600 | 0.069444
A1 | 精密灌装机 | Precision Filling Machine 200m³/h and Automated Conveying Arm 250m³/h | 200 | per hour; divided by 3600 | 0.055556
A2 | 工业清洗机 | High-speed Polishing Machine 100m³/h and Industrial Cleaning Machine250m³/h | 250 | per hour; divided by 3600 | 0.069444
A2 | 高速抛光机 | High-speed Polishing Machine 100m³/h and Industrial Cleaning Machine250m³/h | 100 | per hour; divided by 3600 | 0.027778
A3 | 自动传感多功能机 | Automatic Sensing Multi-Function Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
B1 | 工业清洗机 | Industrial Cleaning Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
B2 | 自动化输送臂 | Precision Filling Machine 200m³/h and Automated Conveying Arm 300m³/h | 300 | per hour; divided by 3600 | 0.083333
B2 | 精密灌装机 | Precision Filling Machine 200m³/h and Automated Conveying Arm 300m³/h | 200 | per hour; divided by 3600 | 0.055556
B3 | 精密灌装机 | Precision Filling Machine 350m³/h | 350 | per hour; divided by 3600 | 0.097222
B4 | 自动传感多功能机 | High-speed Polishing Machine 120m³/h and Automatic Sensing Multi-Function Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
B4 | 高速抛光机 | High-speed Polishing Machine 120m³/h and Automatic Sensing Multi-Function Machine 100m³/h | 120 | per hour; divided by 3600 | 0.033333
C1 | 自动化输送臂 | Industrial Cleaning Machine 250m³/h and Automated Conveying Arm 250m³/h | 250 | per hour; divided by 3600 | 0.069444
C1 | 工业清洗机 | Industrial Cleaning Machine 250m³/h and Automated Conveying Arm 250m³/h | 250 | per hour; divided by 3600 | 0.069444
C2 | 精密灌装机 | Precision Filling Machine 350m³/h | 350 | per hour; divided by 3600 | 0.097222
C3 | 自动化输送臂 | Precision Filling Machine 200m³/h and Automated Conveying Arm 250m³/h | 250 | per hour; divided by 3600 | 0.069444
C3 | 精密灌装机 | Precision Filling Machine 200m³/h and Automated Conveying Arm 250m³/h | 200 | per hour; divided by 3600 | 0.055556
C4 | 工业清洗机 | High-speed Polishing Machine 120m³/h and Industrial Cleaning Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
C4 | 高速抛光机 | High-speed Polishing Machine 120m³/h and Industrial Cleaning Machine 100m³/h | 120 | per hour; divided by 3600 | 0.033333
C5 | 自动传感多功能机 | Automatic Sensing Multi-Function Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
D1 | 工业清洗机 | Industrial Cleaning Machine 250m³/h | 250 | per hour; divided by 3600 | 0.069444
D2 | 自动化输送臂 | Precision Filling Machine 200m³/h and Automated Conveying Arm 300m³/h | 300 | per hour; divided by 3600 | 0.083333
D2 | 精密灌装机 | Precision Filling Machine 200m³/h and Automated Conveying Arm 300m³/h | 200 | per hour; divided by 3600 | 0.055556
D3 | 精密灌装机 | Precision Filling Machine 350m³/h | 350 | per hour; divided by 3600 | 0.097222
D4 | 自动传感多功能机 | High-speed Polishing Machine 120m³/h and Automatic Sensing Multi-Function Machine 300m³/h | 300 | per hour; divided by 3600 | 0.083333
D4 | 高速抛光机 | High-speed Polishing Machine 120m³/h and Automatic Sensing Multi-Function Machine 300m³/h | 120 | per hour; divided by 3600 | 0.033333
D5 | 自动传感多功能机 | Automatic Sensing Multi-Function Machine 300m³/h | 300 | per hour; divided by 3600 | 0.083333
D6 | 高速抛光机 | High-speed Polishing Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
E1 | 工业清洗机 | Industrial Cleaning Machine 250m³/h | 250 | per hour; divided by 3600 | 0.069444
E2 | 精密灌装机 | Precision Filling Machine 350m³/h | 350 | per hour; divided by 3600 | 0.097222
E3 | 工业清洗机 | Automatic Sensing Multi-Function Machine 300m³/h and Industrial Cleaning Machine 100m³/h | 100 | per hour; divided by 3600 | 0.027778
E3 | 自动传感多功能机 | Automatic Sensing Multi-Function Machine 300m³/h and Industrial Cleaning Machine 100m³/h | 300 | per hour; divided by 3600 | 0.083333

## 问题1车间完工
车间 | 完工时间(s) | 完工时间(HH:MM:SS) | 是否最晚完工车间
A | 41600 | 11:33:20 | TRUE

## 问题2车间完工
车间 | 完工时间(s) | 完工时间(HH:MM:SS) | 是否最晚完工车间
D | 152344 | 42:19:04 | TRUE
C | 149204 | 41:26:44 | FALSE
E | 134379 | 37:19:39 | FALSE
B | 105354 | 29:15:54 | FALSE
A | 79209 | 22:00:09 | FALSE

## 问题3车间完工
车间 | 完工时间(s) | 完工时间(HH:MM:SS) | 是否最晚完工车间
C | 123844 | 34:24:04 | TRUE
B | 122929 | 34:08:49 | FALSE
D | 116209 | 32:16:49 | FALSE
A | 109459 | 30:24:19 | FALSE
E | 96189 | 26:43:09 | FALSE

## 问题4车间完工
车间 | 完工时间(s) | 完工时间(HH:MM:SS) | 是否最晚完工车间
C | 123844 | 34:24:04 | TRUE
B | 122929 | 34:08:49 | FALSE
D | 116209 | 32:16:49 | FALSE
A | 109459 | 30:24:19 | FALSE
E | 96189 | 26:43:09 | FALSE

## 问题1设备类型统计
设备类型 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 运输时间占比 | 作业记录数
Automatic Sensing Multi-Function Machine | 1 | 18000 | 200 | 0.43269 | 0.010989 | 1
High-speed Polishing Machine | 1 | 18000 | 200 | 0.43269 | 0.010989 | 1
Industrial Cleaning Machine | 1 | 7200 | 200 | 0.17308 | 0.027027 | 1
Precision Filling Machine | 1 | 5400 | 200 | 0.12981 | 0.035714 | 1
Automated Conveying Arm | 1 | 4320 | 200 | 0.10385 | 0.044248 | 1

## 问题2设备类型统计
设备类型 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 运输时间占比 | 作业记录数
High-speed Polishing Machine | 1 | 135000 | 2605 | 0.88615 | 0.018931 | 7
Automatic Sensing Multi-Function Machine | 1 | 117360 | 3400 | 0.77036 | 0.028155 | 8
Precision Filling Machine | 4 | 88150 | 1590 | 0.14466 | 0.017718 | 10
Industrial Cleaning Machine | 5 | 109728 | 1295 | 0.14405 | 0.011664 | 9
Automated Conveying Arm | 3 | 57840 | 1190 | 0.12656 | 0.020159 | 7

## 问题3设备类型统计
设备类型 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 运输时间占比 | 作业记录数
High-speed Polishing Machine | 2 | 135000 | 2355 | 0.54504 | 0.017145 | 7
Automatic Sensing Multi-Function Machine | 2 | 117360 | 2380 | 0.47382 | 0.019876 | 8
Industrial Cleaning Machine | 5 | 109728 | 1200 | 0.1772 | 0.010818 | 9
Precision Filling Machine | 5 | 88150 | 1200 | 0.14236 | 0.01343 | 10
Automated Conveying Arm | 4 | 57840 | 1000 | 0.11676 | 0.016995 | 7

## 问题4设备类型统计
设备类型 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 运输时间占比 | 作业记录数
High-speed Polishing Machine | 2 | 135000 | 2355 | 0.54504 | 0.017145 | 7
Automatic Sensing Multi-Function Machine | 2 | 117360 | 2380 | 0.47382 | 0.019876 | 8
Industrial Cleaning Machine | 5 | 109728 | 1200 | 0.1772 | 0.010818 | 9
Precision Filling Machine | 5 | 88150 | 1200 | 0.14236 | 0.01343 | 10
Automated Conveying Arm | 4 | 57840 | 1000 | 0.11676 | 0.016995 | 7

## 问题1班组统计
班组 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 作业记录数
班组1 | 5 | 52920 | 1000 | 0.25442 | 5

## 问题2班组统计
班组 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 作业记录数
班组1 | 14 | 508078 | 10080 | 0.23822 | 41

## 问题3班组统计
班组 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 作业记录数
班组1 | 10 | 283026 | 3975 | 0.22853 | 26
班组2 | 8 | 225052 | 4160 | 0.22715 | 15

## 问题4班组统计
班组 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 作业记录数
班组1 | 10 | 283026 | 3975 | 0.22853 | 26
班组2 | 8 | 225052 | 4160 | 0.22715 | 15

## 瓶颈设备类型分析
问题 | 设备类型 | 设备数量 | 总工作时长(s) | 总运输时间(s) | 平均利用率 | 运输时间占比 | 作业记录数
问题1 | Automatic Sensing Multi-Function Machine | 1 | 18000 | 200 | 0.43269 | 0.010989 | 1
问题1 | High-speed Polishing Machine | 1 | 18000 | 200 | 0.43269 | 0.010989 | 1
问题1 | Industrial Cleaning Machine | 1 | 7200 | 200 | 0.17308 | 0.027027 | 1
问题1 | Precision Filling Machine | 1 | 5400 | 200 | 0.12981 | 0.035714 | 1
问题1 | Automated Conveying Arm | 1 | 4320 | 200 | 0.10385 | 0.044248 | 1
问题2 | High-speed Polishing Machine | 1 | 135000 | 2605 | 0.88615 | 0.018931 | 7
问题2 | Automatic Sensing Multi-Function Machine | 1 | 117360 | 3400 | 0.77036 | 0.028155 | 8
问题2 | Precision Filling Machine | 4 | 88150 | 1590 | 0.14466 | 0.017718 | 10
问题2 | Industrial Cleaning Machine | 5 | 109728 | 1295 | 0.14405 | 0.011664 | 9
问题2 | Automated Conveying Arm | 3 | 57840 | 1190 | 0.12656 | 0.020159 | 7
问题3 | High-speed Polishing Machine | 2 | 135000 | 2355 | 0.54504 | 0.017145 | 7
问题3 | Automatic Sensing Multi-Function Machine | 2 | 117360 | 2380 | 0.47382 | 0.019876 | 8
问题3 | Industrial Cleaning Machine | 5 | 109728 | 1200 | 0.1772 | 0.010818 | 9
问题3 | Precision Filling Machine | 5 | 88150 | 1200 | 0.14236 | 0.01343 | 10
问题3 | Automated Conveying Arm | 4 | 57840 | 1000 | 0.11676 | 0.016995 | 7
问题4 | High-speed Polishing Machine | 2 | 135000 | 2355 | 0.54504 | 0.017145 | 7
问题4 | Automatic Sensing Multi-Function Machine | 2 | 117360 | 2380 | 0.47382 | 0.019876 | 8
问题4 | Industrial Cleaning Machine | 5 | 109728 | 1200 | 0.1772 | 0.010818 | 9
问题4 | Precision Filling Machine | 5 | 88150 | 1200 | 0.14236 | 0.01343 | 10
问题4 | Automated Conveying Arm | 4 | 57840 | 1000 | 0.11676 | 0.016995 | 7

## 静态瓶颈设备分析
问题 | 设备类型 | 设备数量 | 理论总负载(s) | 静态负载压力(s/台) | 排名
问题2 | High-speed Polishing Machine | 1 | 135000 | 135000 | 1
问题2 | Automatic Sensing Multi-Function Machine | 1 | 117360 | 117360 | 2
问题2 | Industrial Cleaning Machine | 5 | 109728 | 21945.6 | 3
问题2 | Precision Filling Machine | 5 | 88150 | 17630 | 4
问题2 | Automated Conveying Arm | 4 | 57840 | 14460 | 5
问题3 | High-speed Polishing Machine | 2 | 135000 | 67500 | 1
问题3 | Automatic Sensing Multi-Function Machine | 2 | 117360 | 58680 | 2
问题3 | Industrial Cleaning Machine | 10 | 109728 | 10972.8 | 3
问题3 | Precision Filling Machine | 10 | 88150 | 8815 | 4
问题3 | Automated Conveying Arm | 8 | 57840 | 7230 | 5
问题4 | High-speed Polishing Machine | 2 | 135000 | 67500 | 1
问题4 | Automatic Sensing Multi-Function Machine | 2 | 117360 | 58680 | 2
问题4 | Industrial Cleaning Machine | 10 | 109728 | 10972.8 | 3
问题4 | Precision Filling Machine | 10 | 88150 | 8815 | 4
问题4 | Automated Conveying Arm | 8 | 57840 | 7230 | 5

## 关键任务诊断
问题 | 内部工序编号 | 原始工序编号 | 车间 | 设备编号 | 设备类型 | 起始秒 | 结束秒 | critical_score | 原因
问题1 | A3 | A3 | A | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 23600 | 41600 | 1 | latest_workshop；near_makespan；bottleneck_machine；long_duration
问题1 | A2 | A2 | A | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 5600 | 23600 | 0.7 | latest_workshop；bottleneck_machine；long_duration
问题1 | A2 | A2 | A | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 5600 | 12800 | 0.35 | latest_workshop
问题1 | A1 | A1 | A | Precision Filling Machine1-1 | Precision Filling Machine | 200 | 5600 | 0.35 | latest_workshop
问题1 | A1 | A1 | A | Automated Conveying Arm1-1 | Automated Conveying Arm | 200 | 4520 | 0.35 | latest_workshop
问题2 | D6 | D6 | D | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 127144 | 152344 | 0.956 | latest_workshop；near_makespan；bottleneck_machine；long_duration
问题2 | D4 | D4 | D | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 36744 | 81744 | 0.7 | latest_workshop；bottleneck_machine；long_duration
问题2 | D5 | D5 | D | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 108664 | 126664 | 0.6 | latest_workshop；bottleneck_machine
问题2 | D4 | D4 | D | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 28024 | 46024 | 0.6 | latest_workshop；bottleneck_machine
问题2 | C5-3 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 134804 | 149204 | 0.54382 | near_makespan；bottleneck_machine
问题2 | E3 | E3 | E | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 127179 | 134379 | 0.51462 | near_makespan；bottleneck_machine
问题2 | D3 | D3 | D | Precision Filling Machine1-2 | Precision Filling Machine | 23395 | 28024 | 0.35 | latest_workshop
问题2 | D2 | D2 | D | Precision Filling Machine1-2 | Precision Filling Machine | 8995 | 23395 | 0.35 | latest_workshop
问题2 | D2 | D2 | D | Automated Conveying Arm1-2 | Automated Conveying Arm | 8995 | 18595 | 0.35 | latest_workshop
问题2 | D1 | D1 | D | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 355 | 8995 | 0.35 | latest_workshop
问题2 | C4-3 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 114884 | 126884 | 0.25 | bottleneck_machine
问题2 | C5-2 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 94004 | 108404 | 0.25 | bottleneck_machine
问题2 | B4 | B4 | B | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 94554 | 105354 | 0.25 | bottleneck_machine
问题2 | C4-2 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 82004 | 94004 | 0.25 | bottleneck_machine
问题2 | B4 | B4 | B | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 79719 | 92679 | 0.25 | bottleneck_machine
问题2 | A3 | A3 | A | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 61209 | 79209 | 0.25 | bottleneck_machine
问题2 | C5-1 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 46284 | 60684 | 0.25 | bottleneck_machine
问题2 | C4-1 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 24484 | 36484 | 0.25 | bottleneck_machine
问题2 | A2 | A2 | A | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 5600 | 23600 | 0.25 | bottleneck_machine
问题2 | B2 | B2 | B | Precision Filling Machine1-4 | Precision Filling Machine | 4630 | 31630 | 0.06 | long_duration
问题3 | C5-3 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 109444 | 123844 | 0.9 | latest_workshop；near_makespan；bottleneck_machine
问题3 | C4-3 | C4 | C | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 95044 | 107044 | 0.8593 | latest_workshop；near_makespan；bottleneck_machine
问题3 | C4-3 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 95044 | 109444 | 0.61512 | latest_workshop；near_makespan
问题3 | C5-2 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 74164 | 88564 | 0.6 | latest_workshop；bottleneck_machine
问题3 | C4-2 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 59764 | 71764 | 0.6 | latest_workshop；bottleneck_machine
问题3 | C5-1 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 38884 | 53284 | 0.6 | latest_workshop；bottleneck_machine
问题3 | C4-1 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 24484 | 36484 | 0.6 | latest_workshop；bottleneck_machine
问题3 | D6 | D6 | D | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 91009 | 116209 | 0.5875 | near_makespan；bottleneck_machine；long_duration
问题3 | B4 | B4 | B | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 109969 | 122929 | 0.54778 | near_makespan；bottleneck_machine
问题3 | B4 | B4 | B | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 107594 | 118394 | 0.5368 | near_makespan；bottleneck_machine
问题3 | A3 | A3 | A | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 91459 | 109459 | 0.51515 | near_makespan；bottleneck_machine
问题3 | C3-3 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 88564 | 95044 | 0.35 | latest_workshop
问题3 | C3-3 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 88564 | 93748 | 0.35 | latest_workshop
问题3 | C4-2 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 59764 | 74164 | 0.35 | latest_workshop
问题3 | D4 | D4 | D | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 28009 | 73009 | 0.35 | bottleneck_machine；long_duration
问题3 | C3-2 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 53284 | 59764 | 0.35 | latest_workshop
问题3 | C3-2 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 53284 | 58468 | 0.35 | latest_workshop
问题3 | C4-1 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 24484 | 38884 | 0.35 | latest_workshop
问题3 | C3-1 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 18004 | 24484 | 0.35 | latest_workshop
问题3 | C3-1 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 18004 | 23188 | 0.35 | latest_workshop
问题4 | C5-3 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 109444 | 123844 | 0.9 | latest_workshop；near_makespan；bottleneck_machine
问题4 | C4-3 | C4 | C | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 95044 | 107044 | 0.8593 | latest_workshop；near_makespan；bottleneck_machine
问题4 | C4-3 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 95044 | 109444 | 0.61512 | latest_workshop；near_makespan
问题4 | C5-2 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 74164 | 88564 | 0.6 | latest_workshop；bottleneck_machine
问题4 | C4-2 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 59764 | 71764 | 0.6 | latest_workshop；bottleneck_machine
问题4 | C5-1 | C5 | C | Automatic Sensing Multi-Function Machine1-1 | Automatic Sensing Multi-Function Machine | 38884 | 53284 | 0.6 | latest_workshop；bottleneck_machine
问题4 | C4-1 | C4 | C | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 24484 | 36484 | 0.6 | latest_workshop；bottleneck_machine
问题4 | D6 | D6 | D | High-speed Polishing Machine1-1 | High-speed Polishing Machine | 91009 | 116209 | 0.5875 | near_makespan；bottleneck_machine；long_duration
问题4 | B4 | B4 | B | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 109969 | 122929 | 0.54778 | near_makespan；bottleneck_machine
问题4 | B4 | B4 | B | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 107594 | 118394 | 0.5368 | near_makespan；bottleneck_machine
问题4 | A3 | A3 | A | Automatic Sensing Multi-Function Machine2-1 | Automatic Sensing Multi-Function Machine | 91459 | 109459 | 0.51515 | near_makespan；bottleneck_machine
问题4 | C3-3 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 88564 | 95044 | 0.35 | latest_workshop
问题4 | C3-3 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 88564 | 93748 | 0.35 | latest_workshop
问题4 | C4-2 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 59764 | 74164 | 0.35 | latest_workshop
问题4 | D4 | D4 | D | High-speed Polishing Machine2-1 | High-speed Polishing Machine | 28009 | 73009 | 0.35 | bottleneck_machine；long_duration
问题4 | C3-2 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 53284 | 59764 | 0.35 | latest_workshop
问题4 | C3-2 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 53284 | 58468 | 0.35 | latest_workshop
问题4 | C4-1 | C4 | C | Industrial Cleaning Machine1-1 | Industrial Cleaning Machine | 24484 | 38884 | 0.35 | latest_workshop
问题4 | C3-1 | C3 | C | Precision Filling Machine1-1 | Precision Filling Machine | 18004 | 24484 | 0.35 | latest_workshop
问题4 | C3-1 | C3 | C | Automated Conveying Arm1-1 | Automated Conveying Arm | 18004 | 23188 | 0.35 | latest_workshop

## 问题4候选搜索说明
参数 | 值
budget | 500000
min_price | 35000
candidate_count | 11
coarse_iterations | 2
medium_iterations | 4
refine_iterations | 8
medium_k | 3
top_k | 2
max_candidates_per_type | 6
local_search_attempts | 20
bottleneck_local_search_attempts | 20
workers | 2
decoder | mixed
bottleneck_types | 高速抛光机；自动传感多功能机；工业清洗机
bottleneck_guided | TRUE
sa_t0 | 100
sa_alpha | 0.9997
tabu_tenure | 7

## 问题4候选购置方案对比
排名 | 购买总费用 | 当前搜索最优可行时长(s) | 当前搜索最优可行时长(HH:MM:SS) | 班组1购买方案 | 班组2购买方案 | 新购设备利用率 | 是否通过可行性检查
1 | 0 | 123844 | 34:24:04 | 不购买 | 不购买 | 0 | TRUE
2 | 35000 | 123844 | 34:24:04 | 不购买 | 精密灌装机x1 | 0 | TRUE
3 | 35000 | 123844 | 34:24:04 | 精密灌装机x1 | 不购买 | 0 | TRUE
4 | 40000 | 123844 | 34:24:04 | 不购买 | 工业清洗机x1 | 0 | TRUE
5 | 40000 | 123844 | 34:24:04 | 工业清洗机x1 | 不购买 | 0 | TRUE
6 | 50000 | 123844 | 34:24:04 | 不购买 | 自动化输送臂x1 | 0 | TRUE
7 | 50000 | 123844 | 34:24:04 | 自动化输送臂x1 | 不购买 | 0 | TRUE
8 | 75000 | 123844 | 34:24:04 | 不购买 | 高速抛光机x1 | 0.56684 | TRUE
9 | 75000 | 123844 | 34:24:04 | 高速抛光机x1 | 不购买 | 0.56684 | TRUE
10 | 80000 | 123844 | 34:24:04 | 不购买 | 自动传感多功能机x1 | 0.16279 | TRUE
11 | 80000 | 123844 | 34:24:04 | 自动传感多功能机x1 | 不购买 | 0.16279 | TRUE

## C工序展开说明
配置项 | 配置值 | 说明 | 原始工序编号 | 内部展开编号 | 车间 | 工程量 | 所需设备类型 | 展开原因说明
是否启用C工序展开 | TRUE | --no-expand-c 关闭
展开集合 | C3、C4、C5 | C3-C5
展开次数 | 3 | 每个原始工序展开次数
|  |  | C3 | C3-1 | C | 360 | 自动化输送臂 + 精密灌装机 | C3-C5重复工程段内部展开
|  |  | C3 | C3-2 | C | 360 | 自动化输送臂 + 精密灌装机 | C3-C5重复工程段内部展开
|  |  | C3 | C3-3 | C | 360 | 自动化输送臂 + 精密灌装机 | C3-C5重复工程段内部展开
|  |  | C4 | C4-1 | C | 400 | 工业清洗机 + 高速抛光机 | C3-C5重复工程段内部展开
|  |  | C4 | C4-2 | C | 400 | 工业清洗机 + 高速抛光机 | C3-C5重复工程段内部展开
|  |  | C4 | C4-3 | C | 400 | 工业清洗机 + 高速抛光机 | C3-C5重复工程段内部展开
|  |  | C5 | C5-1 | C | 400 | 自动传感多功能机 | C3-C5重复工程段内部展开
|  |  | C5 | C5-2 | C | 400 | 自动传感多功能机 | C3-C5重复工程段内部展开
|  |  | C5 | C5-3 | C | 400 | 自动传感多功能机 | C3-C5重复工程段内部展开